## Slide 1
Jun 2025
Portfolio Overview
Summary
SYSTRA
Project Name | Status | Mood | Risk | Progress | Program
Mise en place d'un outil de com' inApp | Finished | - | ● | 66% | Industrialiser nos process
Remplacement du système de paiement | Solution Chosen | ● | ● | 56% | Industrialiser nos process
Lancement du marché Espagnol | Ongoing Sourcing | ● | ● | 54% | Programme Gamma
Management de la gestion des stocks | In Progress | ● | ● | 0% | Programme Gamma
Ticket restau dématérialisés | Arbitrage | - | ● | 10% | Programme performance 2024
Industrialisation de nos KPI métier | Solution Chosen | ● | ● | 53% | Programme performance 2024
Nouveau plan de compétence | Solution Chosen | ● | ● | 53% | Programme performance 2024
Legend: Mood: ● Good ● Complicated ● Blocked | Risk: ● Low ● Medium ● High

## Slide 2
Jun 2025
Project review : Com' inApp
1
SYSTRA
DESCRIPTION & EXPECTED BENEFITS
▪
Améliorer la connaissance des fonctionnalités plateforme pour augmenter l'engagement utilisateur.
SCOPE & MILESTONES
▪
Deployment area: Direction generale
▪
Progress: 66% complete
▪
End users: Platform users
▪
Timeline: Aug 2024 - Oct 2024
PROGRESS
▪
Status: Finished
▪
Milestone progress: 0%
▪
Goal: Améliorer l'engagement des clients
NEXT STEPS
▪
Project completed - monitoring phase
▪
Evaluate user engagement metrics
▪
Plan potential enhancements
DECISIONS
Made :
▪
Va-t-on plus loin sur ce POC ? - Study phase
▪
Go / no go ? - Must have decision pending
RISKS & STATUS
▪
Risk Level: ● Low
▪
Importance: Life Changing
▪
Owner: Magalie AirSaas (PMO)
TRENDS
Scope ▲
Schedule ▲
Budget ▲
BUDGET
Build
▪
BAC : 500 K€ (Dev, Integration, hosting, maintenance, support)
▪
Actual : 245 K€
▪
EAC : 245 K€

## Slide 3
Jun 2025
Project review: Com' inApp
2
SYSTRA
BUDGET DETAILS
Type | Initial | Planned | Consumed | Landing
CAPEX (FY2025) | 500 K€ | 500 K€ | 245 K€ | 245 K€
OPEX (FY2025) | 1,240 K€ | 1,240 K€ | 0 K€ | 0 K€
PROJECT TEAM
▪
Product Owner: Magalie AirSaas (PMO)
▪
Sponsor: bertran ruiz (DG)
▪
PMO: Marisella Pacheco (Responsable Produit Design)
See the link: Followup budget file

## Slide 4
Jun 2025
Com' inApp - Planning
3
SYSTRA
PLANNING
Project Timeline: Aug 1, 2024 - Oct 16, 2024
66% Complete
Key Milestones:
•
1er quarter plan sur le périmètre choisi - In Progress (40%)
•
Acheter les licenses - In Progress (7%)
•
Ajustements post-pilote - To Do
Program: Industrialiser nos process par des méthodes et des outils
TEAM WORKLOAD IN M/D
 | Projet/Offre | IT Sécu | IT Infra | Transfo | Total
Budget (m/d) | - | - | - | - | -
Used (m/d) | - | - | - | - | -
To do (m/d) | - | - | - | - | -

## Slide 5
Jun 2025
Project review : Système de paiement
4
SYSTRA
DESCRIPTION & EXPECTED BENEFITS
▪
Remplacer l'outil historique coûteux par une solution moderne avec données analytiques sur les transactions.
SCOPE & MILESTONES
▪
Deployment area: DSI
▪
Milestone progress: 55%
▪
End users: All departments
▪
Timeline: May 2022 - Sep 2026
PROGRESS
▪
Status: Solution Chosen
▪
Overall progress: 56%
▪
Effort: 206 m/d planned, 15 m/d used
NEXT STEPS
▪
Complete Mollie integration setup
▪
Finalize data migration plan
▪
User acceptance testing
DECISIONS
Made :
▪
Avancer le lancement de 1 mois - Under study
▪
Decision maker: Dominique Rocheteau
RISKS & STATUS
▪
Risk Level: ● High
▪
Risque d'arrêt de fonctionnement du service - API change imminent
▪
Alerte équipes DATA - audit timing issue
TRENDS
Scope ▼
Schedule ▼
Budget ▼
BUDGET
Build
▪
BAC : 78 K€ (Dev, Integration, hosting, maintenance, support)
▪
Actual : 15 K€
▪
EAC : 68 K€

## Slide 6
Jun 2025
Project review: Système de paiement
5
SYSTRA
BUDGET DETAILS
Budget Line | Planned | Consumed | Landing
Set up Mollie | 57 K€ | 10 K€ | 48 K€
Licences Mollie | 30 K€ | 10 K€ | 30 K€
Etude de faisabilité | 21 K€ | 5 K€ | 20 K€
PROJECT TEAM
▪
Owner: Maxime Exterisa (Chef de projet transverse)
▪
Sponsor: bertran ruiz (DG)
▪
PMO: Emilie Delpante (PMO DSI)
See the link: Followup budget file

## Slide 7
Jun 2025
Système de paiement - Planning
6
SYSTRA
PLANNING
Project Timeline: May 2, 2022 - Sep 30, 2026
56% Complete
Key Milestones:
•
1er quarter plan sur le périmètre choisi - In Progress (40%)
•
Acheter les licenses - In Progress (7%)
•
Ajustements post-pilote - To Do
Expected Benefits: Diminution des coûts de transaction de 10%, fluidité UX, nouveau contrat
TEAM WORKLOAD IN M/D
 | Services gén. | Dir. Opé. | Maintenance | IT DATA | Total
Budget (m/d) | - | - | - | - | 206
Used (m/d) | - | - | - | - | 15
To do (m/d) | - | - | - | - | 191

## Slide 8
Jun 2025
Project review : Marché Espagnol
7
SYSTRA
DESCRIPTION & EXPECTED BENEFITS
▪
Expansion vers l'Espagne pour diversifier les revenus et renforcer la présence internationale.
SCOPE & MILESTONES
▪
Deployment area: Direction generale
▪
Milestone progress: 66%
▪
End users: Spanish market
▪
Timeline: Jan 2025 - Dec 2025
PROGRESS
▪
Status: Ongoing Sourcing
▪
Overall progress: 54%
▪
Effort: 148 m/d planned
NEXT STEPS
▪
Identify key local partners
▪
Structure commercial offer
▪
Adapt product for Spanish market
DECISIONS
Made :
▪
Go / no go ? - Must have, deadline Jan 31, 2026
▪
Decision maker: bertran ruiz (DG)
RISKS & STATUS
▪
Risk Level: ● Medium
▪
Mood: ● Blocked
▪
Owner: Simon Vacher (CPO)
TRENDS
Scope -
Schedule ▼
Budget -
BUDGET
Build
▪
BAC : 150 K€ (Dev, Integration, hosting, maintenance, support)
▪
Actual : - K€
▪
EAC : - K€

## Slide 9
Jun 2025
Project review: Marché Espagnol
8
SYSTRA
BUDGET DETAILS
Type | Initial | Planned | Consumed | Landing
CAPEX (FY2025) | 150 K€ | - | - | -
OPEX (FY2025) | 5 K€ | 5 K€ | - | -
PROJECT TEAM
▪
Owner: Simon Vacher (CPO)
▪
Sponsors: Arnold Bigair (PM), Matthieu Delanoë (CTO)
▪
PMO: Emilie Delpante (PMO DSI)
▪
Business Lead: bertran ruiz (DG)
See the link: Followup budget file

## Slide 10
Jun 2025
Marché Espagnol - Planning
9
SYSTRA
PLANNING
Project Timeline: Jan 2, 2025 - Dec 31, 2025
54% Complete
Key Milestones:
•
1er quarter plan sur le périmètre choisi - In Progress (40%)
•
Acheter les licenses - In Progress (7%)
•
Ajustements post-pilote - To Do
Program: Programme Gamma
TEAM WORKLOAD IN M/D
 | Mkt-data | Transfo | Projet/Offre | IT Sécu | Total
Budget (m/d) | 30 | 40 | 60 | 18 | 148
Used (m/d) | - | - | - | - | -
To do (m/d) | 30 | 40 | 60 | 18 | 148

## Slide 11
Jun 2025
Project review : Gestion des stocks
10
SYSTRA
DESCRIPTION & EXPECTED BENEFITS
▪
Remplacer l'outil obsolète par un SaaS moderne pour réduire la maintenance et les coûts de 20%.
SCOPE & MILESTONES
▪
Deployment area: DSI
▪
Milestone progress: 32%
▪
End users: Inventory teams
▪
Timeline: Mar 2024 - Jan 2025
PROGRESS
▪
Status: In Progress
▪
Overall progress: 0%
▪
Effort: 200 m/d planned, 5 m/d used
NEXT STEPS
▪
Complete SaaS vendor selection
▪
Data migration planning
▪
User training preparation
DECISIONS
Made :
▪
Go / no go ? - Must have decision pending
▪
Decision maker: bertran ruiz (DG)
RISKS & STATUS
▪
Risk Level: ● Medium
▪
Mood: ● Good
▪
Owner: Alfred Matthieu (Tester)
TRENDS
Scope -
Schedule -
Budget -
BUDGET
Build
▪
BAC : - K€ (Dev, Integration, hosting, maintenance, support)
▪
Actual : - K€
▪
EAC : - K€

## Slide 12
Jun 2025
Project review: Gestion des stocks
11
SYSTRA
BUDGET DETAILS
Type | Initial | Planned | Consumed | Landing
CAPEX | - | - | - | -
OPEX | - | - | - | -
PROJECT TEAM
▪
Owner: Alfred Matthieu (Tester)
▪
Sponsor: Benedek Zsargó (Developer)
▪
Business Leads: Alex Lamy (PM), Jérôme D. (Content Manager), Marisella Pacheco
See the link: Followup budget file

## Slide 13
Jun 2025
Gestion des stocks - Planning
12
SYSTRA
PLANNING
Project Timeline: Mar 3, 2024 - Jan 10, 2025
0% Complete
Key Milestones:
•
1er quarter plan sur le périmètre choisi - In Progress (40%)
•
Acheter les licenses - In Progress (7%)
•
Ajustements post-pilote - To Do
Goals: Améliorer l'expérience utilisateur, Devenir data driven
TEAM WORKLOAD IN M/D
 | Encaissement | Transfo | Mkt-data | AirSaas | IT DATA | Total
Budget (m/d) | 40 | 40 | 20 | 10 | 10 | 200
Used (m/d) | - | - | - | 5 | - | 5
To do (m/d) | 40 | 40 | 20 | 5 | 10 | 195

## Slide 14
Jun 2025
Project review : Ticket restau
13
SYSTRA
DESCRIPTION & EXPECTED BENEFITS
▪
Système de tickets restaurants dématérialisés pour réduire les coûts et simplifier les processus.
SCOPE & MILESTONES
▪
Deployment area: Direction generale
▪
Milestone progress: 84%
▪
End users: All employees
▪
Timeline: Jun 2025 - Jul 2026
PROGRESS
▪
Status: Arbitrage
▪
Overall progress: 10%
▪
Effort: 66 m/d planned, 6 m/d used
NEXT STEPS
▪
Vendor selection finalization
▪
Integration with HR systems
▪
Employee communication plan
DECISIONS
Made :
▪
Go / no go ? - Must have decision pending
▪
Decision maker: bertran ruiz (DG)
RISKS & STATUS
▪
Risk Level: ● Low
▪
Mood: -
▪
Owner: Alex Lamy (PM)
TRENDS
Scope -
Schedule -
Budget -
BUDGET
Build
▪
BAC : 5 K€ (Dev, Integration, hosting, maintenance, support)
▪
Actual : 7.5 K€
▪
EAC : - K€

## Slide 15
Jun 2025
Project review: Ticket restau
14
SYSTRA
BUDGET DETAILS
Type | Initial | Planned | Consumed | Landing
CAPEX | 5 K€ | - | 7.5 K€ | -
OPEX | 150 K€ | - | - | -
PROJECT TEAM
▪
Owner: Alex Lamy (PM)
▪
Teams: Marketing - Offre, Marketing - data, Transfo et méthode, Maintenance
See the link: Followup budget file

## Slide 16
Jun 2025
Ticket restau - Planning
15
SYSTRA
PLANNING
Project Timeline: Jun 12, 2025 - Jul 9, 2026
10% Complete
Key Milestones:
•
1er quarter plan sur le périmètre choisi - In Progress (40%)
•
Acheter les licenses - In Progress (7%)
•
Ajustements post-pilote - To Do
Goals: Améliorer l'expérience utilisateur, Recruter 200 personnes
TEAM WORKLOAD IN M/D
 | Mkt-data | Maintenance | Transfo | Mkt-Offre | Total
Budget (m/d) | 30 | 21 | 15 | - | 66
Used (m/d) | 0 | 5 | 1 | - | 6
To do (m/d) | 30 | 16 | 14 | - | 60

## Slide 17
Jun 2025
Project review : KPI métier
16
SYSTRA
DESCRIPTION & EXPECTED BENEFITS
▪
Automatiser les métriques avec consolidation automatique pour un reporting cohérent et homogène.
SCOPE & MILESTONES
▪
Deployment area: Transfo et méthode
▪
Milestone progress: 14%
▪
End users: All departments
▪
Timeline: Apr 2025 - Mar 2026
PROGRESS
▪
Status: Solution Chosen
▪
Overall progress: 53%
▪
Effort: 90 m/d planned, 40 m/d used
NEXT STEPS
▪
Define common reference framework
▪
Implement automated collection
▪
Dashboard development
DECISIONS
Made :
▪
Va-t-on plus loin sur ce POC ? - Under study
▪
Decision maker: bertran ruiz (DG)
RISKS & STATUS
▪
Risk Level: ● Medium
▪
Mood: ● Complicated
▪
Owner: Matthieu Delanoë (CTO)
TRENDS
Scope -
Schedule ▼
Budget ▼
BUDGET
Build
▪
BAC : 75 K€ (Dev, Integration, hosting, maintenance, support)
▪
Actual : 50 K€
▪
EAC : 77 K€

## Slide 18
Jun 2025
Project review: KPI métier
17
SYSTRA
BUDGET DETAILS
Type | Initial | Planned | Consumed | Landing
CAPEX (FY2026) | 75 K€ | 75 K€ | 50 K€ | 77 K€
OPEX (FY2026) | 12 K€ | 12 K€ | 10 K€ | 10 K€
PROJECT TEAM
▪
Owner: Matthieu Delanoë (CTO)
▪
Product Owners: sarah Thiebault, Simon Vacher, Thomas Poitau
▪
PMO: Audrey Anselmoz
See the link: Followup budget file

## Slide 19
Jun 2025
KPI métier - Planning
18
SYSTRA
PLANNING
Project Timeline: Apr 1, 2025 - Mar 1, 2026
53% Complete
Key Milestones:
•
1er quarter plan sur le périmètre choisi - In Progress (40%)
•
Acheter les licenses - In Progress (7%)
•
Ajustements post-pilote - To Do
Goals: Réduire dépenses immo 40%, Améliorer UX interne, Devenir data driven
TEAM WORKLOAD IN M/D
 | Mkt-Offre | Maintenance | Transfo | IT Sécu | IT Appli | Total
Budget (m/d) | 10 | 10 | 10 | 10 | 50 | 90
Used (m/d) | 2 | 2 | 1 | 5 | 30 | 40
To do (m/d) | 8 | 8 | 9 | 5 | 20 | 50

## Slide 20
Jun 2025
Project review : Plan compétence
19
SYSTRA
DESCRIPTION & EXPECTED BENEFITS
▪
Améliorer le staffing RH et Marketing avec prise en compte des éléments financiers et simulations.
SCOPE & MILESTONES
▪
Deployment area: Direction generale
▪
Milestone progress: 38%
▪
End users: RH, Marketing/Com
▪
Timeline: Jan 2024 - Jan 2025
PROGRESS
▪
Status: Solution Chosen
▪
Overall progress: 53%
▪
Effort: 30 m/d planned, 3 m/d used
NEXT STEPS
▪
Finalize staffing module
▪
Integration with financial systems
▪
User training rollout
DECISIONS
Made :
▪
Go / no go ? - Must have decision pending
▪
Decision maker: bertran ruiz (DG)
RISKS & STATUS
▪
Risk Level: ● Medium
▪
Mood: ● Good
▪
Owner: Emilie Delpante (PMO DSI)
TRENDS
Scope ▲
Schedule -
Budget -
BUDGET
Build
▪
BAC : 100 K€ (Dev, Integration, hosting, maintenance, support)
▪
Actual : 0.5 K€
▪
EAC : - K€

## Slide 21
Jun 2025
Project review: Plan compétence
20
SYSTRA
BUDGET DETAILS
Type | Initial | Planned | Consumed | Landing
CAPEX | 100 K€ | - | 0.5 K€ | -
OPEX | 1.2 K€ | - | 1 K€ | -
PROJECT TEAM
▪
Owner: Emilie Delpante (PMO DSI)
▪
Sponsors: Jean Claude La rue, Benedek Zsargó, Emilie Delpante
▪
Business Leads: bertran ruiz (DG), Thomas Merlot (Production director)
See the link: Followup budget file

## Slide 22
Jun 2025
Plan compétence - Planning
21
SYSTRA
PLANNING
Project Timeline: Jan 7, 2024 - Jan 10, 2025
53% Complete
Key Milestones:
•
1er quarter plan sur le périmètre choisi - In Progress (40%)
•
Acheter les licenses - In Progress (7%)
•
Ajustements post-pilote - To Do
Expected Benefits: Meilleure prise en compte staffing RH, meilleure ergonomie, autonomie métier
TEAM WORKLOAD IN M/D
 | IT DATA | AirSaas | Maintenance | IT Sécu | IT Appli | Total
Budget (m/d) | - | - | 20 | 5 | 5 | 30
Used (m/d) | - | - | 2 | 1 | 0 | 3
To do (m/d) | - | - | 18 | 4 | 5 | 27

## Slide 23
Jun 2025
Data Notes
22
SYSTRA
FIELDS NOT DIRECTLY MAPPED
The following template fields had no direct data mapping and were populated with derived or default values:
•
report_date: Set to current month (Jun 2025)
•
followup_budget_link: Placeholder link used
•
bac, actual, eac: Derived from budget_capex, budget_capex_used, budget_capex_landing
•
trend_scope, trend_schedule, trend_budget: Inferred from project risk and mood indicators
•
budget_m_d_* fields: Mapped from efforts array where team names matched
•
used_m_d_* fields: Mapped from effort_used in efforts array
•
to_do_m_d_* fields: Calculated as budget - used
Projects with limited budget data:
•
Management de la gestion des stocks - No budget values defined
•
Nouveau plan de compétence - Budget values not per fiscal year
•
Ticket restau dématérialisés - Budget values not per fiscal year
Note: All milestones shown are from the global milestones array and may include milestones from related projects within the same program.